## MASTER
ELECTION TASKS | RESPONSIBLE | START PERIOD | NOTES
Determine Ballot Numbers with Town Clerk | ROV | 2012-09-05 | Meet with Town Clerk to order # of ballots
Minor Party Nominations | ROV | 2012-09-05 | For state, district and municipal office - made and certified.
Memory Cards | ROV | 2012-09-10 | Send to LHS and determine appropriate number for election day
Sample Absentee Ballots Available | Informational | 2012-09-15 | Registrar may also direct TC to send blank ballots to out of country , Servicemen, who have applied for absentee ballot
Registration by Mail | ROV and DROV | 2012-09-18 | 10 DAY Acceptance or Rejection Letters through 10/16
Submit Academy Building Community Use | ROV | 2012-09-18 | This can also be done at the beginning of the year
Submit Community Use applications for Polls | ROV | 2012-09-18 | This can also be done at the beginning of the year
Polling Stations - How many lines | ROV | 2012-09-18 | See Preliminary schedule of Pollworkers
Phone Lines | ROV | 2012-09-18 | Verify all polling locations have phone lines
Select Training Dates | ROV | 2012-09-18 | This can also be done earlier than this date of the year
Reserve Meeting Rooms for Training | ROV | 2012-09-18 | This can also be done earlier than this date of the year
Prepare Pollworker training schedule | ROV | 2012-09-18 | This is driven by how you train - all poll workers at the same time or separately based on the job the poll worker is performing
Notice of corrections for Preliminary Registry List | ROV | 2012-09-20 | Notice will be published on
Notify TC re: AB's Central Count | ROV | 2012-09-20
Questions on the Ballot | Informational | 2012-09-21 | Last day to provide to SOS order and how will appear on ballot* for municipal election
Supervised Balloting | ROV | 2012-09-22 | Start of period through 10/30/12 for written designation and supervisor for location requiring supervised balloting- only where there are <20 electors
Notify Election workers of hire/ give training dates | ROV | 2012-09-26 | phone with Training Dates and Make-up date
SOTS PHONE CONFERENCE RE. PREPARE FOR ELECTIONS | ROV and DROV | 2012-09-27 | 1:00 pm CALL 1-888-398-9603 Password: VOTER
Update TOG Web site | DROV | 2012-09-30 | include on home page, ballot, etc.
OCT
Challenged Registrations | ROV | 2012-10-01 | Last day to mail challenge as to retention of name on registry
SPECIAL SESSION: PRELIMINARY REGISTRY LIST | DROV | 2012-10-02 | Session held between 3:00 pm and 5:00 pm as deemed necessary
Mechanics / ROV Meeting | ROV | 2012-10-03
Notify Town Clerk of the registration status | DROV | 2012-10-03 | tell Town Clerk dates of acceptance of walk-in, mail reg.
Hire AB Workers and Health Care Asst Reg | ROV | 2012-10-03 | Supervised balloting
Polling Places | ROV | 2012-10-05 | Last day to determine polling places for the election
Contact Capitol Moving, Mark Gagnon | Mary | 2012-10-05 | Dates for moving equipment/Can be done earlier
Begin Testing and Charging Battery Back-ups and Scanners | MECHANICS | 2012-10-10
Notify TC re: AB's Central Count | ROV | 2012-10-10 | Memo of schedule for training, ck-off, counting & rooms
Notice to Paper re. Special Registration Session | ZL | 2012-10-12 | For Citizen - Saturday, October 20, 2012 10 am to 2 pm Special Session
Tab Tender Training / Ballot Clerk Training | ROV | 2012-10-12 | Friday at 11:00 am
Prepare AB Moderator Return | DROV | 2012-10-14 | Prepared for Moderator Training on October 16th
Registration by Mail | ROV and DROV | 2012-10-16 | Last day 4 DAY Acceptance or Rejection Letters
Checkers Training | ROV | 2012-10-16 | Tuesday at 11:00 am
AB Training | ROV | 2012-10-16 | Tuesday at 3:00 pm
List of Election Officials Complete | ROV | 2012-10-16
Notify Candidates re: Voting Machine ballot inspect | ROV | 2012-10-16 | Party Chairs, Candidates re: machine inspect
START Same day acceptance ltrs re. registration to vote | ROV and DROV | 2012-10-17 | Letters accepting registration must be sent same day.
Supervised Balloting | ROV | 2012-10-17 | Mountain Laurel at 11:00 am Salmon Brook Nursing Home 2:00 pm
Load Storage Bins | ROV | 2012-10-17
Prepare Election Officials badges | Deputy | 2012-10-17
Test Memory Cards for FORMATTING | DROV | 2012-10-18
Pick up Sandwich Board to advertise | DROV | 2012-10-18 | Pick up from Laura Perry, 3rd Flr, Town Hall
Verify poll set-up supplies | ROV | 2012-10-18 | Correct signs, forms, ballots, tape etc.
Supervised Balloting | ROV | 2012-10-19 | Herbert T. Clark House @ 12:30 pm
Notice to Paper re. 10/30/12 | ZL | 2012-10-19 | OCTOBER 30, 2012 REGISTRATION SESSION 9 AM to 8 PM
SATURDAY REGISTRATION DAY | ROV & DROV | 2012-10-20 | Open for registration 10:00 am to 2:00 pm
Notice to Paper re. 10/30/12 | ZL | 2012-10-22 | 2ND notice re. OCTOBER 30, 2012 REGISTRATION SESSION
Supervised Balloting | ROV | 2012-10-23 | Glastonbury Health Center 1:30 pm
Assistant Registrar Training | ROV | 2012-10-23 | Tuesday, 10:30 am
Write - In registration - last day to register w/SOS | Informational | 2012-10-23
New Registrations: Last Day to accept Mail-In Registration | ROV and DROV | 2012-10-23 | LAST DAY Reg By Mail-in Postmarked by 10/23
LAST DAY Same day acceptance ltrs re. registration to vote | ROV and DROV | 2012-10-23 | Letters accepting registration must be sent same day.
Deadline for requests for special registration session | ROV | 2012-10-23 | Supervised balloting for >25 persons employed by same employee, or at same school, or nursing home etc. make a written request for on site voter registration
Availability Period to make corrections to registry | DROV | 2012-10-23 | Starts on the 23rd and must be completed by November 5
Asst. Reg. Training | ROV | 2012-10-23 | Tuesday, 10:30 am
Prepare Moderator's Return | DROV | 2012-10-23 | Prepared for Moderator Training on October 25th
Last Day for Write-In Candidates to register with SOTS | SOTS | 2012-10-23 | ROVs to be on look out for list of write-in candidates
Registration by Mail after 10/24 - after election privilege | ROV and DROV | 2012-10-24 | Privilege attaches after 11/6/12 Election
Certification of Tabulator | ROV and DROV | 2012-10-24 | Certification begins after 5:00 pm
Contact Police Dept. Traffic Officer | ROV | 2012-10-25
Moderator Training | ROV | 2012-10-25 | Thursday at 10:30 am
Conference Call | ROV and DROV | 2012-10-25 | 1-888-398-9603 password: voter
Notice to paper re. Limited registration on 11/05/12 | ZL | 2012-10-26 | Notice that this is last day to register
Confirm lunch food orders: pick-up X | ROV | 2012-10-26 | Pick-up/delivery schedule for Mechanics to polls
Complete Supervised Balloting at H.C. Centers | ROV | 2012-10-30 | Both ROVs or reps must be present for process
Conference Call | ROV and DROV | 2012-10-31 | 1-888-398-9603 password: voter Happy Halloween!
Special Registration; names removed | DROV and ROV | 2012-11-01 | All day from 9:00 AM until 8:00 PM-adjusted per Gov. Malloy
Communicate polls set-up schedule | ROV | 2012-11-01 | Notify all Town, BOE contacts & Mechanics
Make-up Training for all positions | ROV | 2012-11-01 | 18:00
Prepare OFFICIAL VOTER LISTS (Active and Inactive) | DROV | 2012-11-02 | 3 (one-sided) copies required
Distribute Lists |  | 2012-11-02 | to Town Clerk- AB apps:alpha w/TOG districts listed
NOV
Prepare Moderator's boxes/food bags | DROV | 2012-11-02 | Have the food bags complete
Delivery of Voting Machines | MECHANICS | 2012-11-02 | Deliver machines, privacy booths, IVS, tubs, banker boxes with materials for moderators, poll supplies
AB checkoff | AB | 2012-11-02 | Friday at 10:30 am - First Checkoff
AB checkoff | AB | 2012-11-05 | Monday at 1:00 pm - Second Checkoff
Prepare Supplemental Voting List | Deputy | 2012-11-05 | Verify all updates & run reports after 5:00 PM
Polls set-up All Mechanics & ROVs | Mechanics & ROV | 2012-11-05 | Set-up polls with ALL Mechanics
Reconcile Voter Numbers on Official Lists; sign ALL | ROV | 2012-11-05 | Final totals per district for active voters to MOD'S
Meet with Moderators | ROV | 2012-11-05 | Set up appts after 6:00 pm
Process ballot count & CERTIFY recpt from Town Clerk | AB MOD | 2012-11-05
ELECTION DAY | ROV | 2012-11-06 | Polls open 6 am till 8 pm
Visit Polls on Election Day to ensure processing OK | ROV | 2012-11-06
AB Counting on Election Day | AB | 2012-11-06 | Tuesday at 1:00 pm until completed
Close the polls | MECHANICS | 2012-11-06
File Head Moderator Return | ROB and DROV | 2012-11-06 | Email to ted.bromley@ct.gov
One Memory Card per Polling Place to UCONN | DROV | 2012-11-07 | Per newsletter from SOTS - send after pre-election testing
File Training Certification form with Town Clerk/SOS | ROV | 2012-11-07
Return all Polling Equipment w/ Capitol Moving | Mechanics | 2012-11-07 | Return Machines/ Booths to Town Hall
Update TOG Web site: election results | DROV | 2012-11-07
Review PollWorker Official's hours for PayRoll | ROV | 2012-11-08
Prepare thank you letters & send w/check | ROV | 2012-11-09

## Job Sort
ELECTION TASKS | RESPONSIBLE | START PERIOD | NOTES
Lottery Selection | ROV | 2011-08-22 | Lottery at 1:00 pm by ROVs
Process ballot count & CERTIFY recpt from Town Clerk | AB MOD | 2011-11-07 | AB Mod certifies AB count to Head Moderator
Hire AB Workers; and Health Care Assist Reg | AB ROV | 2011-09-15 | Hire Mod, Asst Mod, Checker/counters and Hlth Care
Determine schedule for AB check/counters | AB ROV | 2011-09-22 | check-off days (2); 11/03, 11/7
AB checkoff | AB ROV | 2011-11-03 | AB's do check-off
AB checkoff | AB ROV | 2011-11-07 | Final AB Checkoff
SPECIAL SESSION: Preliminary List Check | ALL ROV | 2011-10-04 | Hours: 12:00 - 2:00 PM Prelim List Active & Inactive
SPECIAL SESSION: Saturday 10/22/11 | ALL ROV | 2011-10-22 | HOURS: 10:00 AM-2:00 PM
Special Session LAST DAY In-Person Reg 11/1/11 | ALL ROV | 2011-11-01 | ALL DAY 9 am - 8pm
New registrations; acceptance notices = 4 DAYS | Deputy | 2011-09-20 | 4 DAY NOTICE 09/20/11-10/17/11
Distribute active/inactive lists (alpha) | Deputy | 2011-09-25 | to Town Clerk- AB apps:alpha w/TOG districts listed
Prepare Preliminary voting list | Deputy | 2011-09-27 | Place Book at Info Center
Prepare Preliminary voting list | Deputy | 2011-10-05 | Post Prelim List in Town Hall Information Area
Prepare Inactive Voting List for correction | Deputy | 2011-10-06 | List for corrections 10/04/05
New registrations: NOTICE = SAME DAY | Deputy | 2011-10-19 | SAME DAY 10/19/2007-10/25/11
Registration by Mail after 10/25 After Election Privilege | Deputy | 2011-10-24 | Privilege attach after 11/7 Election Day
New Registrations: Last Day to accept Mail-In Regist | Deputy | 2011-10-25 | LAST DAY Reg By Mail-ins Postmarked by 10/25
Prepare Election Officials badges | Deputy | 2011-10-30 | Also for unofficial checkers if required
Prepare Inactive Voting List | Deputy | 2011-11-02
Prepare OFFICIAL VOTER LISTS | Deputy | 2011-11-02 | 3 copies required for all including parties
Prepare Moderator Forms & supplies for Polls | Deputy | 2011-11-02
Registry List Filed with TC | Deputy | 2011-11-02 | Corrected/ Updated Voting List
Verify Corrcted Official Lists to Town Clerk | Deputy | 2011-11-02 | Post with Town Clerk's Office
Prepare Moderator's boxes/food bags | Deputy | 2011-11-03 | Determine supplies/ buy as needed
SPECIAL SESSION: MATURED RIGHTS | Deputy | 2011-11-07 | HOURS 9am-12 noon MATURED RIGHTS only since 10/25
Prepare Supplemental Voting List | Deputy | 2011-11-07 | Verify all updates & run before 5:00 PM
Choose ReCanvass Date | Head Moderators | 2011-11-13 | Check w calculators
Begin Testing and Charging Battery Back-ups and Scanners | MECHANICS | 2011-09-15 | Testing Equipment
Voting Machine Checkups | Mechanics | 2011-10-06 | Alan Tinti and John DiSette
Prepare Machines Charge & Certify | Mechanics | 2011-10-15 | Charge batteries, will certify with ROVs
Delivery of Voting Machines | MECHANICS | 2011-11-04 | Deliver machines, Privacy Booths; IVS; Tubs and Banker Boxers Materials for Moderators, Poll Supplies
Ensure Voting Mach moved w/ Mechanics | MECHANICS | 2011-11-04 | Moving van & mechanic's support as scheduled
Election Day: Close of Polls | MECHANICS | 2011-11-08 | Take Down Privacy booths; secure Tabulators & IVS
Return all Polling Equipment w/ Capitol Moving | Mechanics | 2011-11-09 | Return Machines/ Booths to Town Hall
Polls set-up All Mechanics & ROVs | Mechanics & ROV | 2011-11-07 | Set-up polls with ALL Mechanics
Submit Academy school use | ROV | 2011-08-08 | Contact Parks/Rec for facility
Submit Community Use applications for Polls | ROV | 2011-08-08 | Note: school use limitations per site
Contact Capitol Moving, Mark Gagnon | ROV | 2011-08-10 | Dates for moving equipment
Select Training dates: reserve rooms | ROV | 2011-09-01 | Council, meeting A; confirmed with Town Clerk
Determine Ballot numbers with Town Clerk | ROV | 2011-09-06 | Meet with Town Clerk to order # of balltos
AB facilities Mail Letters re: AB applications | ROV | 2011-09-15 | Packages mailed ABfacilities:GHC, Salmon Brk Hebron Ave
VERIFY NEW PHONE/FAX LINES IVS | ROV | 2011-09-16 | Mechanics will verify
Prepare Pollworker training schedule | ROV | 2011-09-19 | Mechanics to attend ?
Confirm volume of machines/locations | ROV | 2011-09-21 | Determine polls w/multiple lines etc
ROVAC Conference: Danbury | ROV | 2011-09-21 | Fall Conference 9/21 and 9/22
Notify TC re: AB's Central Count | ROV | 2011-09-25 | Memo of schedule for training, ck-off, counting & rooms
Meeting w/ Machine Mechanics schedule | ROV | 2011-09-26 | 11 AM Meeting to disucss Technicians Tasks and dates
Notify Election workers of hire/ give training dates | ROV | 2011-09-27 | Mail letters with Training Dates and ONE Make-up
Set dates for Training of Poll Workers | ROV | 2011-10-01 | Reserve Chambers, Conf Room A with Judy
Review/update training Power Point Presentation | ROV | 2011-10-03 | MUST INCLUDE NEW LAWS' INFORMATION
Contact Engineering Dept (Chuck) | ROV | 2011-10-05 | Need UNOFFICIAL Ballot Poster Size
Notify Town Manager Posting of Lists | ROV | 2011-10-05 | Reminder to Town Manager
FILE w/SOS: Polling Place Certif w Moderator Info | ROV | 2011-10-07 | Poll Info & Moderator Info name address contact info and district info with each (Cong, Fed, State and Muni)
FILE w/SOS: Ballot Certification Numbers | ROV | 2011-10-07 | w Town Clerk jointly certify to SOS the # of ballots ordered for each poll per form provided from SOS w/ past election info
Absentee Ballots Ready for Public | ROV | 2011-10-07 | Available at Town Clerk's office
Post Preliminary Lists: Active, Inactive, Off lists | ROV | 2011-10-07 | Set-up LISTS in TOG Info Center (Approve R. Johnson)
Preliminary ACTIVE list to Town Clerk | ROV | 2011-10-07 | Certified list from both ROV to Town Clerk
Special Session: Revise and Corrected List | ROV | 2011-10-12 | 1 - 3 pm Session to Revise & Correct Preliminary Registry List
Begin Pollworker Training class certify all workers | ROV | 2011-10-12 | 10/12; 10/14; 10/18; 10/20 Make-up 10/24
Order food - ALL election workers | ROV | 2011-10-15 | Numbers for each poll, ROV office
Preliminary ACTIVE lists: DISTRIBUTE | ROV | 2011-10-17 | Certified list: give candidates as requested
Start facilities' AB voting | ROV | 2011-10-19 | Asst Reg teams, per each political party 10/19; 21 and 26
Verify poll set-up supplies | ROV | 2011-10-20 | Correct signs, forms, ballots, tape etc.
Notify Candidates re:Voting Mach ballot inspect | ROV | 2011-10-23 | Party Chairs, Candidates re: machine inspect
Training make-up class | ROV | 2011-10-24 | Class: all election officials who missed training class
Contact Police Dept. Traffic Officer | ROV | 2011-10-27
Certification of tabulators | ROV | 2011-10-27 | Start machine test: 10/27 W Mechanics if need 10/28
Certified Corrected Registry List to Town Clerk | ROV | 2011-10-28 | Certify Copy for Town Clerk
Complete AB voting @ Health Care Centers; Del to TC | ROV | 2011-10-30 | Both ROV's or reps. must be present for process
Registration & Party Enrollment Form ED 651 to SOS | ROV | 2011-10-30 | Faxed or Hand Del's by Nov 7, 2011
Schedule polls' set-up meeting w/Mech.&/Town Maintenance Staff | ROV | 2011-11-01 | Determine any poll location revisions for all
Communicate polls set-up schedule | ROV | 2011-11-01 | Notify all Town, BOE contacts & Mechanics
Provide AB Training | ROV | 2011-11-02 | Notify Town Clerk for check-off processing
Confirm lunch food orders: pick-up X | ROV | 2011-11-03 | Pick-up/delivery schedule for Mechanics to polls
Confirm poll locations to TOG Staff | ROV | 2011-11-04 | Parking in backlots
Unofficial Checkers List Notification to ROV | ROV | 2011-11-04 | Must Notify ROV prior to 6am 11/4/11
File Training Certification form with Town Clerk/SOS | ROV | 2011-11-07
Reconcile Voter Numbes onOfficial Lists; sign ALL | ROV | 2011-11-07 | Final totals per district for active voters to MOD'S
Review PollWorker Official's hours for PayRoll | ROV | 2011-11-07
Visit Polls to ensure processing OK | ROV | 2011-11-07
Prepare thank you letters & send w/check | ROV | 2011-11-10
Send thank-you notes to institutions | ROV | 2011-12-05
Reserve Meeting rooms for Training | ROV | 2011-08-15 | See Schedule
Update TOG Web site with election data | TCB | 2011-09-10 | Special sessions & poll Locations/voting hours
Update TOG Web site: election results | TCB | 2011-11-09
Notice: Citizen 8/12 (BALLOT LOTTERY) | ZL | 2011-08-12 | Submitt to Citizen for 8/17 Publication for Lotery Date 8/22
Notice: Citizen: Town Clerk Preliminary List Posting | ZL | 2011-09-21 | Post in Citizen that Preliminary List Posted on 10/5
Notice: Citizen SpS Add or Correct Prelim on 10/04/11 | ZL | 2011-09-21 | Add or Correct Prelim Regsitry List 10/4 held 12 - 2 PM
Notice: Citizen SpS to Revise & Correct Registry 10/12/11 | ZL | 2011-09-21 | Revised & Corrected Regsitry List 10/12 held 1-3 PM
Notice: Citizen Applications for Registration | ZL | 2011-10-06 | Applications for Registration to Vote Notice 25+
Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM
Notice: Citizen Polling Locations | ZL | 2011-10-11 | FYI: POLLING Locations/Hours
Notice: Citizen Special Session 11/1 Last Day toRegister | ZL | 2011-10-11 | Special session ALL DAY 11/1 9:00 AM - 8:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM | Notice: Citizen of Special Sessions 10/22 | ZL | 2011-10-06 | Special session Sat 10/22/11 10:00 AM-2:00 PM
Notice: Citizen RE: Matured Rights Session 11/7/11 & Second Polling locations | ZL | 2011-10-20 | Matured Rights from 10/25 thru 11/7 Session 9 AM - 12 PM

## Citizen Notices
ELECTION TASKS | RESP | START DAY | START PERD | APPEAR CITIZEN | NOTES
Notice: Citizen 8/12 (BALLOT LOTTERY) | ZL |  | 2012-09-21 | 2012-09-27 | Submitt to Citizen for 8/17 Publication for Lotery Date 8/22
Notice to Town Clerk RE: Special Sessions | ZL |  | 2011-09-21 | 2011-09-27 | Post in Citizen that Preliminary List Posted on 10/5
Notice: Citizen SpS Add or Correct Prelim on 10/02/11 | ZL | Friday | 2012-09-21 | 2012-09-27 | Add or Correct Prelim Regsitry List 10/2 from 3 to 5 PM
Notice: Citizen SpS to Revise & Correct Registry 10/12/11 | ZL |  | 2011-09-21 | 2011-09-27 | Revised & Corrected Regsitry List 10/12 held 1-3 PM
Notice: Citizen Applications for Registration | ZL |  | 2011-10-06 | 2011-10-12 | Applications for Registration to Vote Notice 25+
Notice: Citizen of Special Sessions 10/20 | ZL | Friday | 2012-10-05 | 2012-10-11 | Special session Sat 10/20/12 10:00 AM-2:00 PM
Notice: Citizen Polling Locations | ZL |  | 2011-10-11 | 2011-10-19 | FYI: POLLING Locations/Hours
Notice: Citizen Special Session 11/1 Last Day to Register | ZL |  | 2011-10-11 | 2011-10-20 | Special session ALL DAY 11/1 9:00 AM - 8:00 PM
Notice: Citizen RE: Matured Rights Session 11/7/11 & Second Polling locations | ZL |  | 2011-10-20 | 2011-10-27 | Matured Rights from 10/25 thru 11/7 Session 9 AM - 12 PM