## Slide 1: Preparing for election
Timeline to managing elections effectively

## Slide 2
PUTTING ON YOUR EVENT PLANNING HAT

## Slide 3: PUTTING ON YOUR EVENT PLANNING HAT
SECURE YOUR FACILITIES
DETERMINE PERSONNEL NEEDS
IDENTIFY WHAT ELECTION MATERIALS ARE NEEDED
ESTABLISH A TIMELINE IN WHICH TO ACCOMPLISH THE TASKS

## Slide 4: SECURE YOUR FACILITIES
Time Frame
  Reserve facilities anywhere from 9 months out to no later than THREE MONTHS OUT
    At least 1 months out test the facilities
      Phone line
      Electrical outlets for tabulators and IVS
Determine if counting Absentee Ballots centrally and secure rooms

## Slide 5: Election Equipment required at each polling location
Election Equipment –
  Make sure all Tabulators are available and operational 3-6 months out as well as batteries
  Check IVS equipment – within one month of the election
  Make sure have sufficient stantions, stands for signs and other aids to assist voters as to where they go ONE MONTH out

## Slide 6: Determine Personnel Needs
Hire Poll Workers
  Planning starts beginning of every year or after each election
    Evaluate your current poll workers
    Make sure your moderators are certified and, if not, schedule training for them
    Start hiring poll workers THREE MONTHS in advance
    Poll staffing is statutory with deadlines
      Certify polling locations and provide moderator addresses no later than October 4, 2019
      October 15 is last day to appoint election officials

## Slide 7: Personnel continued
Required to train all poll workers before each election
  Set up training schedule no more than ONE MONTH before every election
  Establish a back up date for those who are unable to make the first meeting
  Provide by email a copy of the training material

## Slide 8: Materials to support an election
BALLOTS
  THREE MONTHS
    Update historical information on ballots ordered and turnout ie in municipal election what is typical turnout, how many current voters do you have and determine number of ballots including test ballots.
MEMORY CARDS
  THREE MONTHS
    Make sure all cards are with LHS for programming

## Slide 9: Election Materials continued
THREE MONTHS out
  Review supplies including
    Paper
    Pens for voters at the polls
    Folders
    Signage

## Slide 10: Getting the word out
Town Website
  Update THREE MONTHS out anticipation of Election
  Review important dates for requiring newspaper notifications ie
    Notice of special Session to update the voter list has to be in the paper no later than September 25, 2019
  TWO MONTHS out notify candidates and political parties reminding of election rules re 75 foot lines and bathroom usage

## Slide 11: Election Time
Two months out
Supervised Balloting
  Notify Supervised Balloting facilities of impending election
  Set up dates to conduct supervised balloting within THREE WEEKS of the Election not later than week before the election

## Slide 12: Election time paperwork and reporting system updates
Moderator Books and Boxes
  Create documents for use in the polls and for election night reporting
    ONE MONTH out set up
      Tally Sheets
      Moderator Books
      Oaths
      Timesheets
Election Night Reporting ONE MONTH out
  Update Election management system

## Slide 13: Election Time Training and Testing
Testing
  Test the memory cards and seal tabulators within two weeks of the Election but no later than 10 days before the election.
  Test the IVS equipment
Training
  Within the month before the election
  Remember with EDR to schedule CVRS training
    Will have to establish sign on access 2 weeks in advance

## Slide 14: DETAILS FOR ELECTION DAY
Order food – within one month of election
Transport election equipment to the polling locations – one to four days in advance
Visit polling locations the day before the election
Meet with Moderators night before the election and ensure they have all necessary materials